## Trend by Month
| UID Watch | Data
| Deliverable2 |  | Deliverable1 |  | Total Average of Work | Total Average of Baseline Work
Status Month | Average of Work | Average of Baseline Work | Average of Work | Average of Baseline Work
2012-05 | 325 | 328 | 563.0208 | 568 | 444.0104 | 448
2012-06 | 297.213 | 328 | 568.5469 | 568 | 432.8799 | 448
2012-07 | 240.4266 | 328 | 559.0755 | 568 | 399.751 | 448
2012-08 | 211.8792 | 328 | 578.1656 | 568 | 395.0224 | 448
2012-09 | 204.7 | 328 | 599.9578 | 568 | 402.3289 | 448
2012-10 | 206.8271 | 328 | 636.0323 | 568 | 421.4297 | 448
2012-11 | 202.4521 | 328 | 680.6842 | 568 | 441.5681 | 448
2012-12 | 194.4521 | 328 | 629.1781 | 568 | 411.8151 | 448
2013-01 | 190.4375 | 328 | 554.8875 | 568 | 372.6625 | 448
2013-02 | 190.1875 | 328 | 555.799 | 568 | 372.9932 | 448
2013-03 | 189.4375 | 258.7188 | 548.9083 | 558.4542 | 369.1729 | 408.5865
Grand Total | 216.9272 | 320.8942 | 591.677 | 567.0209 | 404.3021 | 443.9576

## Trend by Week
| UID Watch | Data
| Deliverable2 |  | Deliverable1 |  | Total Sum of Work | Total Sum of Baseline Work
Status Week | Sum of Work | Sum of Baseline Work | Sum of Work | Sum of Baseline Work
2012KW22 | 325 | 328 | 563.0208 | 568 | 888.0208 | 896
2012KW23 | 322.3792 | 328 | 571.5208 | 568 | 893.9 | 896
2012KW24 | 292.6896 | 328 | 570.9 | 568 | 863.5896 | 896
2012KW25 | 286.9083 | 328 | 565.8917 | 568 | 852.8 | 896
2012KW26 | 286.875 | 328 | 565.875 | 568 | 852.75 | 896
2012KW27 | 283.875 | 328 | 567.875 | 568 | 851.75 | 896
2012KW28 | 231.6333 | 328 | 557.9542 | 568 | 789.5875 | 896
2012KW29 | 231.6333 | 328 | 561.4646 | 568 | 793.0979 | 896
2012KW30 | 214.5646 | 328 | 549.0083 | 568 | 763.5729 | 896
2012KW31 | 214.5646 | 328 | 568.0083 | 568 | 782.5729 | 896
2012KW32 | 214.5646 | 328 | 568.0083 | 568 | 782.5729 | 896
2012KW33 | 209.1937 | 328 | 585.0083 | 568 | 794.2021 | 896
2012KW35 | 209.1937 | 328 | 591.6375 | 568 | 800.8313 | 896
2012KW36 | 207.1937 | 328 | 596.1667 | 568 | 803.3604 | 896
2012KW37 | 207.2021 | 328 | 596.6771 | 568 | 803.8792 | 896
2012KW38 | 200.2021 | 328 | 596.0542 | 568 | 796.2563 | 896
2012KW39 | 204.2021 | 328 | 610.9333 | 568 | 815.1354 | 896
2012KW40 | 206.2021 | 328 | 614.5625 | 568 | 820.7646 | 896
2012KW41 | 206.2021 | 328 | 618.5625 | 568 | 824.7646 | 896
2012KW42 | 209.9521 | 328 | 650.8125 | 568 | 860.7646 | 896
2012KW43 | 204.9521 | 328 | 660.1917 | 568 | 865.1438 | 896
2012KW45 | 206.9521 | 328 | 665.8896 | 568 | 872.8417 | 896
2012KW46 | 206.9521 | 328 | 668.0187 | 568 | 874.9708 | 896
2012KW47 | 206.9521 | 328 | 682.8979 | 568 | 889.85 | 896
2012KW48 | 196.9521 | 328 | 685.3375 | 568 | 882.2896 | 896
2012KW49 | 194.4521 | 328 | 701.2771 | 568 | 895.7292 | 896
2012KW50 | 194.4521 | 328 | 704.0875 | 568 | 898.5396 | 896
2012KW51 | 194.4521 | 328 | 554.2687 | 568 | 748.7208 | 896
2013KW02 | 190.4375 | 328 | 547.7208 | 568 | 738.1583 | 896
2013KW03 | 190.4375 | 328 | 558.4708 | 568 | 748.9083 | 896
2013KW04 | 190.4375 | 328 | 558.4708 | 568 | 748.9083 | 896
2013KW06 | 190.4375 | 328 | 558.0958 | 568 | 748.5333 | 896
2013KW07 | 190.4375 | 328 | 558.0958 | 568 | 748.5333 | 896
2013KW08 | 190.4375 | 328 | 558.0958 | 568 | 748.5333 | 896
2013KW09 | 189.4375 | 328 | 548.9083 | 568 | 738.3458 | 896
2013KW10 | 189.4375 | 328 | 548.9083 | 568 | 738.3458 | 896
2013KW11 | 189.4375 | 328 | 548.9083 | 568 | 738.3458 | 896
2013KW12 | 189.4375 | 189.4375 | 548.9083 | 548.9083 | 738.3458 | 738.3458
2013KW13 | 189.4375 | 189.4375 | 548.9083 | 548.9083 | 738.3458 | 738.3458
Grand Total | 8460.1604 | 12514.875 | 23075.4021 | 22113.8167 | 31535.5625 | 34628.6917

## Source
UID | Task Name | Work | Finish | Baseline Work | Baseline Finish | Status Week | Filename | Status Month | Status Year | IsSummary | swaImportant | Deliverable | (Sub-)Project | UID Watch

## Config
Project Plans | Import yes/no | Status Week | Status Month | Status Year | UID | Name
C:\some-path\some-plan-in-week-XY.mpp | no | 2012KW22 | 2012-05 | 2012 | 5 | Deliverable1
C:\some-path\some-plan-in-week-XY.mpp | no | 2012KW23 | 2012-06 | 2012 | 7 | Deliverable2
C:\some-path\some-plan-in-week-XY.mpp | no | 2012KW24 | 2012-06 | 2012
C:\some-path\some-plan-in-week-XY.mpp | no | 2012KW25 | 2012-06 | 2012
C:\some-path\some-plan-in-week-XY.mpp | no | 2012KW26 | 2012-06 | 2012
C:\some-path\some-plan-in-week-XY.mpp | no | 2012KW27 | 2012-07 | 2012
C:\some-path\some-plan-in-week-XY.mpp | no | 2012KW28 | 2012-07 | 2012
C:\some-path\some-plan-in-week-XY.mpp | no | 2012KW29 | 2012-07 | 2012
C:\some-path\some-plan-in-week-XY.mpp | no | 2012KW30 | 2012-07 | 2012
C:\some-path\some-plan-in-week-XY.mpp | no | 2012KW31 | 2012-08 | 2012
C:\some-path\some-plan-in-week-XY.mpp | no | 2012KW32 | 2012-08 | 2012
C:\some-path\some-plan-in-week-XY.mpp | yes | 2012KW33 | 2012-08 | 2012